## Risk Assessment
Risks |  |  |  |  | Response | Objective
Description | Consequences | Probability | Impact | Risk Rating
Lack of programming knwledge | Inability to deliver project | Low | High | Moderate | Continue training | Gain enough understanding of java to deliver project
Infected by covid-19 | Sick and ability to learn course and deliver project affected | Low | Moderate/High | Moderate | Self-isolating, social distancing | Avoid infection
Leaking of Database access information | Exposure of database to outside access and potential malicious actions | Low | High | Moderate | Not putting details in any areas where it could be accessible e.g. github | Continued security of DB
GCP instance failure | Panic | Very Low | Very High | High | Gain understanding of GCP to trouble shoot | Learn GCP usage
GCP Credit running out | Inability to access uploaded database | Low | Moderate | Low | Monitor GCP usage and add credit if required | Keep GCP accessible
Falling behind milestones | Project failure/ marked down due to late submissions of work | Low | High | Moderate | Keep to milestones laid out in specification. Use Kanban board to control keep track of project objectives and their status. | Consistent workflow to complete project on time and meet milestones
Failures in code | Program not functioning as inteded | Moderate | Very High | High | Use Code Repository (GitHub) to manage codebase with ability to pull past versions. | Good code keeping
No credentials/ login to change database | Anyone can change orders in system without tracking | Moderate | High | Moderate | Add a User login step so only users with login details can access and edit the database | Secure Database
No comments or notes as work is done | Hindered ability to present project at conclusion or potential confusion when changing code | Low | Low | Low | Add comments as code is updated and keep notes of important parts of the project | Good record keeping and clear path to conclusion of project at end
Damage to computer or drive | Loss of data, namely notes, code and other project related files. | Low | High | Moderate | Upload files to cloud services (GitHub, Onedrive) to ensure some version of the project still exists and can be worked on | Prevent permanent loss of data